Development objective:

A system that delivers quality health care efficiently and equitably and that guarantees social welfare for all has been established.

| Output No | Description of Outputs and Objective |  | Stakeholders |  | Milestone Deliverables | Critical Assumptions and Risks |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Immediate objectives: Policy framework and legal framework which govern Health Care Waste Management in Lesotho are in place. |  | MCA-Lesotho MoHSW (EHD, HR, Finance & Procurement, Technical Health Services, Clinical Services, Legal Services) DHMTs HC Facilities (Hospitals and Clinics) CHAL, Red Cross Society (LRCS) Blood Transfusion Services (BTS) Central Laboratory Services (CLS) National Drug Services Organisation (NDSO) MTEC (NES) MoLG&C MFDP MoPWT M Natural Resources Water and Sewerage Authority (WASA) Maseru City Council (MCC) COWMAN and NHCWM Committees Private Industry Other Consulting Firms, especially HSS |  | 1.1 Situational Analysis Report 1.2 HCWM Policy developed and approved 1.3 Updated National Health Care Waste Management Plan developed and approved 1.4. Regulations on HCWM written and adopted 1.5 HCWM Standards written 1.6 HCWM Guidelines written 1.7 Monitoring, Evaluation and EM systems integrated with HSS Component. 1.8 Licensing and Accreditation procedures for HCWM developed | Consultation and Visits: That all counterpart staff at all levels will be made available at the programmed times for meetings, workshops, field visits etc. That Working groups are established and participants are committed. Situational Analysis; Effective use of available resources is used to visit every hospital. Assumed that hospitals and clinics are accessible at the required times. Policy Document: That the Hazardous & Non-hazardous Waste Bill is finalized & definitions agreed; that the GOL remains committed and the policy document is adopted within the time period. HCWM Plan: Pre-determined technologies for treatment could limit the options for improvement in the short term. That the plan is agreed within the deliverable schedule time period; that GOL remains committed and sufficient funds are made available to implement the plan Regulations. That the Hazardous & Non-hazardous Bill is finalized and that the process for adopting the regulations is within the deliverable schedule time period. If this is not possible that commitment is made from MoTEC to include a schedule on HCRW into the final Waste Bill once that is ready, and that the MoTEC actively participates in the development and drafting of the Schedule on HCRW Standards and Guidelines, Monitoring and Evaluation, Licensing and accreditation: Co-operation with HSS Component: That HSS Firm is committed financially to carry the costs of HCRW print materials and training as indicated in the ToR of the HCRW Firm; that time is coordinated to meet all the deliverables scheduled for the time period. That the inconsistency in the ToR is addressed That the Decentralisation process is successfully implemented and that the DHMT’s staff are motivated. |  |
| Output No |  | Description of Outputs and Objective |  | Stakeholders | Milestone Deliverables |  | Critical Assumptions and Risks |
| 2 |  | Ministry of Health and Social Welfare, the line Ministries and the District Health Management Teams have the capacity to implement and sustain proper Health Care Waste Management in Lesotho and its Health Care Facilities |  | As above | 2.1 Institutional arrangements for HCW agreed in HCWMP 2.2 MoHSW provided with tools to implement proper HCWM system 2.3 HCWM Courses designed and implemented 2.4 HCWM System introduced in Pilot sites 2.5 Exit Strategy elaborated and evaluated |  | Co-operation with HSS Component: That HSS Firm is committed financially to carry the costs of HCRW print materials and training as indicated in the ToR of the HCRW Firm and time period of the two projects are coordinated to meet all the deliverables scheduled. At the moment there is inconsistency in the ToRs of the two projects that need to be resolved. HSS Component have sufficient budget to produce the necessary documents Pilots: That the a pilot conducted in 10 hospitals and 30 Clinics could result in superficial implementation and that the staff at the pilot HC Facilities will be committed and available Exit Strategy: That financial and human capacity within the MoHSW is sufficient and available to sustain the systems developed and agreed to implement the exit strategy and that GOL independently introduce HCWM system in line with NHCWMP in non-pilot HCFs and continue to support and monitor the system |
| 3 |  | The public in general and staff of Health Care Facilities in particular are aware of the legal framework governing Health Care Waste Management as well as of proper Health Care Waste Management Practices. |  | As Above | 3.1 – 3.4 Proper Health Care Waste Management Practices used in HCFs and by the general public using the health care facilities or those residing within the vicinity of health care facilities |  | That HSS Firm is committed financially to carry the costs of HCRW print materials and training as indicated in the ToR of the HCRW Firm and time is coordinated to meet all the deliverables schedule for the time period. At the moment there is inconsistency in the ToRs of the two projects that need to be resolved. HSS Component have sufficient budget to produce all the information packs. |

# LFA – Matrix of Outputs and Stakeholder Analysis

Output 1 :  			Policy and Legal Framework

Immediate Objective 1 :   A Policy and Legal framework to govern Health Care Waste Management in Lesotho is in place

| Output No | Description of Outputs and Objective | Stakeholders | Stakeholder input | Indicators |  | Critical Assump-tions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Means of Verification | Milestone Deliverable |  |
| 1.1 | Situational Analysis is conducted and report prepared giving recommenda-tions for improvement Objective: Identify the institutional aspects, systems and key constraints /opportunities to inform the other outputs with the focus on sustainable change | MCA-Lesotho MoHSW (EHD, HR, Finance & Procurement, Technical, Clinical Services, Legal Services, NDSO) DHMTs HC Facilities (Hospitals and Clinics) CHAL, LRCS BTS; CLS MTEC (NES) MoLG&C MFDP MoPWT M Natural Resources WASA Maseru CC Private Industry Other Consulting Firms e.g. HSS Firm | Information as required made available including: - HC Sector development plans and socio-economic forecasts made available - HR Training plans - Management organograms - Information on Private service providers - Budget and financial planning information Meetings, visits and workshops. - Meetings and visits approved and appointments made - Local Councils and HCFs informed of the programme for visits - Relevant persons available for meetings and site visits - Invitations sent out for workshops - Relevant persons attend workshops | 1.1.1 Programme of visits to all hospitals and sample of urban an rural clinics drafted and appointments booked 1.1.1 Base line study conducted 1.1.1 HCW Treatment and Disposal technologies assessed 1.1.1 Assessment of existing treatment technologies 1.1.2 Socio-economic forecasts 1.1.2 HCW Generation forecasts 1.1.3 Impacts described 1.1.4 Assessment of Capacity in HC sector 1.1.5 Assessment of the capacity of the Private Sector 1.1.6 Recommendations for improvement given 1.1.6 Stakeholder workshop conducted 1.1.6 Action Plan drafted | Situational Analysis Report | That every hospital will be accessible and staff available at the programmed time Consultants will get full access to Health Care Facilities. Staff of HCFs able and willing to cooperate That all the facilities will be accessible at the planned time Doing a Base Line study in all hospitals is inefficient use of available resources |

| Output No | Description of Outputs and Objective | Stakeholders | Stakeholder input | Indicators |  | Critical Assump-tions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Means of Verification | Milestone Deliverable |  |
| 1.2 | HCWM Policy is developed and approved Objective; To prepare a strategic document that will give a framework for the HCWM Plan | As above, including specifically” NES MoHSW DG for Technical Health Services, PS & Minister for approval COWMAN and NHCWM Committees | - Relevant national and MoHSW policy documents made available - Hazardous and non-hazardous Bill made available - Stakeholders informed and made available for input and approval - Stakeholder invitations sent out and attendance assured - Standing / Status of the policy is established - Policy document is approved through relevant approval process | 1.2.1 Policy document prepared for stakeholder input 1.2.2 Consultation workshops conducted with key stakeholders 1.2.2 Stakeholder input included into policy | Final Policy Document Policy Document is agreed and adopted MoHSW | The GOL remains committed and the policy document is adopted within the time period stipulated in the deliverable schedule Time required for the adoption of the policy document is protracted. Hazardous & Non-hazardous Bill is not finalized & definitions not agreed |
| 1.3 | Updated National Health Care Waste Management Plan elaborated and approved Objective: To prepare a comprehensive plan that includes both technical requirements and institutional aspects for the implementation of a proper HCWM System | As Above including: Responsibility for finance, budgeting, procurement and HR Government department for PPP Interventions linked to procurement Infection Control, OH&S Personnel HSS Consultants MoHSW DG for Technical Health Services, PS & Minister for approval | - Informed on the consultation process - HPIU responsible to ensure that all consultative process followed, invitations sent out and arrangements made - Input from IC and OH&S Committees - Stakeholder workshop arranged and invitations sent out | 1.3.1 Outline of plan drawn up 1.3.1. Mini and one-on-on consultations conducted 1.3.1 Stakeholder workshops conducted 1.3.2 Comparison of different Technologies for treatment elaborated. 1.3.3 Proposals for treatment methods 1.3.4 Economic viability and capacity of private sector to outsource 1.3.5 Interventions to upgrade current waste management prepared 1.3.6 & 2.1.1 Analysis of current Institutional Framework. 2.1.2 Proposed mechanism for coordination between institutional stakeholders 2.1.3 Draft document for proposed institutional arrangements drafted 2.1.3 Stakeholder workshop on Institutional arrangements 1.3.7 List of documents described 1.3.8 Financial Plan elaborated 1.3.9 Draft improved and updated NHCWMP 1.3.9 Stakeholder workshops conducted 1.3.9 Stakeholder input included and Plan updated. | Updated NHCWM Plan document NHCWM Plan approved by MoHSW DG Technical Health Services, MCA - HPIU and EH Division. NHCWMP adopted by cabinet | Pre-determined technologies for treatment could limit the options Stakeholders do not attend workshops MoHSW, HPIU and E H Division agree on the Plan. Time required for the adoption of the NHCWMP document is protracted and not within the deliverable schedule time period Government of the Kingdom of Lesotho remains financially and in terms of human resources committed to implement the plan Sufficient funds are made available to implement the plan |
| 1.4 | Regulations on Health Care Waste Management prepared and approved Objective: To provide statutory requirement for compliance to an improved HCWM System. | Working group comprising legal and technical persons from: - MCA-Lesotho - MoHSW (EH & Clinical Services, Legal Services) - MTEC (NES) - MoLG&C - MFDP - MoPWT - M Natural Resources - WASA - Maseru CC Stakeholders consulted include DHMTs HC Facilities CHAL, LRCS BTS; CLS Private Industry | - Working group formulated - Informed on the consultation and Legal process - Available legislation under which the Regulations are to be written identified - HPIU responsible to ensure that all consultative process followed, invitations sent out and arrangements made - Stakeholder workshop arranged and invitations sent out | 1.4.1 HCWM Regulations drafted under identified Act (Bill) as identified by the HPIU 1.4.1 Discussion and workshops conducted with working group 1.4.1 Stakeholder consultations arranged | Final Regulation document Regulation document approved by working group Regulation adopted and placed in Government Gazette | That the Hazardous & Non-hazardous Bill will be finalized Or in the absence of the bill a schedule to the bill can be drafted. Stakeholders do not attend workshops Process for adopting the regulations is protracted and not within the deliverable schedule time period |
| 1.5 | Standards for HCWM prepared Objectives: To provide detailed standards that will give effect to the regulations | As above particularly MTEC (NES) MoHSW, EH, Clinical Services, DHMTs, HC Facilities, CHAL & LRCS, BTS; CLS, NDSO COWMAN & NHCWMC | - Working group formulated - HPIU responsible to ensure that all consultative process followed, invitations sent out and arrangements made - Stakeholder workshop arranged and invitations sent out [HSS Task 1.3: Develop, produce and distribute operational guidelines and manuals for HC service providers and HC facility managers | 1.5.1 Standards drafted in collaboration with working group 1.5.1 Stakeholder consultations arranged 1.8.1 Prerequisites and procedures for the licensing of HCRW Collectors and Treatment facilities drawn up | Standards document Standards approved | That stakeholder can attend workshops, including arranging own transport etc. when required HSS Component is committed financially and time is coordinated to meet deliverable schedule time periods HSS Component have sufficient budget to print required documents. |
| 1.6 | Guidelines and procedures for HCWM in HCFs Objective: To provide detailed guidelines at operation level that will give effect to the regulations | As above particularly MoHSW, EH, Clinical Services, QC Division; DHMTs HC Facilities, CHAL & LRCS, BTS; CLS NDSO COWMAN & NHCWMC HSS Quality Assurance Unit (COHSASA) Clinical Services | - Working group formulated that also includes QA Depts - HPIU responsible to ensure that all consultative process followed, invitations sent out and arrangements made - Stakeholder workshop arranged and invitations sent out [HSS Task 1.3: Develop, produce and distribute operational guidelines and manuals for HC service providers and HC facility managers] | - Guideline documents prepared for different categories of HCW in collaboration with working group 1.6.1 Stakeholders workshop arranged 1.8.3 HCWM Procedures for accreditation of HCFs drawn up | Guideline document Guideline document approved | That stakeholder can attend workshops, including arranging own transport etc. when required HSS Component is committed and time periods of the two projects are coordinated to meet deliverable schedule time period. HSS Component have sufficient budget to print required documents |
| 1.7 | Monitoring, Evaluation and Environmental Management system developed Objective: To provide indicators and monitoring action plans for the evaluation of the HCWM System in HCFs | As above: to be integrated with the HMIS part of the HSS component Compliant with NES requirements for EDMP , as a NIP activity. MoHSW, EH, Clinical Services, WASA DHMTs HC Facilities, CHAL & LRCS COWMAN & NHCWMC | - Working group with HSS Component formulated - HPIU responsible to ensure that all consultative process followed, invitations sent out and arrangements made - Stakeholder workshop arranged and invitations sent out [HSS Task 3.2-3.5: HMIS for HCF managers, DHMTs, Local Councils; M&E plan; review existing HMIS; ICT for HMIS; and capacity building to use HMIS (liaise with Consultant Training Advisor)] | 1.7.1 Indicators identified and data collection needs determined 1.7.1 Consultations conducted with HSS and other stakeholders 1.7.2 Environmental Monitoring and Action plan for HCWM drafted at operational level for DHMTs 1.7.2 Workshops conducted with DHMTs on the drafted EM and Action Plan for HCWM (Link with 2.2 Filing procedures and reporting channels) | Indicators provided for the integrated Monitoring System of HSS Component EM & Action plan for DHMTs | There is strong cooperation and coordination between the HSS Component and the HCWM Project HSS Component is committed and time is coordinated to meet deliverable schedule time periods |
| 1.8 | Licensing and accreditation procedures developed Objective: To formalize and license the collection and treatment facilities To link HCWM Procedures in with the QA in clinical services dept. | As above, esp: HCRW Generators HCRW Collectors HCRW Treatment facilities QA Unit of Clinical Services (COHSASA) MoHSW and MoTEC Legal Services DG in Health Services/NES for issuing licences? | - Establish Working group with NES (link to 1.4) - Establish Working group with MOHSW for issuing of licensing including COWMAN & NHCWMC - Establish a Working Group that includes QA Department MoHSW (COHSASA) | 1.8.1 Prerequisites and procedures for the licensing of HCRW Collectors and Treatment facilities drawn up (Link with 1.4 and 1.5.1 Standards) 1.8.2 Requirements for HCFs to obtain a license. 1.8.2 Coordinate with the DG responsible for issuing licenses to private practitioners 1.8.3 HCWM Procedures for accreditation of HCFs drawn up (Link in with 1.6.1) | Licensing and accreditation procedures developed and approved | Working groups are established and working That HCWM licensing and accreditation will link with HSS Comp. ToR. Licensing will link with the Regulations or Schedule to the Hazardous and Non-Hazardous Waste Bill. Licensing is linked with the Standards Developed |

Output 2 :  			Capacity Building and Knowledge Transfer

Immediate Objective 1 :	MoHSW, the line Ministries and the DHMTs have the capacity to implement and sustain proper HCW Management in Lesotho and its HC Facilities

| Output No | Description of Outputs and Objective | Stakeholders | Stakeholder input | Indicators |  | Critical Assump-tions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Means of Verification | Milestone Deliverable |  |
| 2.1 | Institutional arrangements for HCWM agreed | See Output 1.3 | (Included in 1.3 Updated HCWMP) | See Output 1.3 | Institutional arrangements agreed in HWWM Plan (Output 1.3) | The MoHSW approve the institutional arrangement in time That the MoHSW actively implements and supports the institutional arrangments agreed |
| 2.2 | Tools and procedures provided to improve institutional memory Objective: Filing proc / reporting channels are improved. Institutional memory is improved through HSS Component | As above HSS component HMIS | - Establish Working Group that includes HSS component and Department responsible for Health Management Information System [HSS Task 2.1-2.3: Support effective decentralised HS delivery: mentoring, training, support, technical, performance indicators; clarification of roles. HSS Task 3.2-3.5: HMIS for HCF managers, DHMTs, Local Councils; M&E plan; review existing HMIS; ICT for HMIS; and capacity building to use HMIS (liaise with Consultant Training Advisor)] | 2.2.1 Based on standards and procedures developed in 1.4.1; and 1.5.1 and reporting requirements of 1.3 2.2.1 Set of tools developed and consulted with HSS 2.2.2 Linked to output 1.7 EM System tools 2.2.2 Procedures developed for improved institutional memory | Tools for implementing HCWM Procedures for improved institutional memory | There is strong cooperation and coordination between the HSS Component and the HCWM Project HSS Component is committed and time is coordinated to meet deliverable schedule time periods |
| 2.3 | MoHSW is able to implement the NHCWMP Objective: To support and build capacity within the MoHSW and the Line Ministries to sustain, monitor and enforce the policies and standards established. | MoHSW, Line Ministries and DHMTs and HC Facility staff HR Depts HSS Component | - Stakeholders are informed of meetings and one-on-one consultations [HSS Task 1.1: 5-yr in-service and Continuing Education Implementation Programme] | 2.3.1 Skills assessment (Linked to HSS Component) 2.3.2 Individual Development plans. (Link with HSS Component) |  | There is strong cooperation and coordination between the HSS Component and the HCWM Project |
|  |  | MoHSW, Line Ministries and DHMTs and HC Facility staff | - HPIU responsible to identify learners send out invitations and made other arrangements for the courses. [HSS Task 1.2: Implementation of training; Task 1.3: Develop, produce and distribute resource materials, guidelines and manuals] | 2.3.3.Draft course designed 2.3.3 HCWM Course conducted 2.3.3 Learners assessed 2.3.3 Follow up course designed 2.3.3 Follow up training conducted | Basic HCWM Course and follow up courses designed and implemented. | Learners are available to attend training courses, have transport and can be accommodated if necessary GOL continue to ensure support and resources after the Compact agreement has ended. |
|  |  |  |  | 2.3.4 Areas to receive training identified 2.3.4 Plan for skills development devised. |  |  |
|  |  | EH Department DHMTs, CHAL & LRCS QA Department | - Assist with the identification of the pilot sites - Obtain QA inspection plan [HSS Task 2.1-2.3: Support effective decentralised HS delivery: mentoring, training, support, technical, performance indicators; clarification of roles] [HSS Task 3.2-3.5: HMIS for HCF managers, DHMTs, Local Councils; M&E plan; review existing HMIS; ICT for HMIS; and capacity building to use HMIS (liaise with Consultant Training Advisor)] | 2.3.5 Pilot plan devised 2.3.6 Monitoring plan implemented in pilot sites 2.3.7 Assistance given with compliance inspections at one hospital 2.3.7 Findings report of monitoring and inspection available |  | Scope of the piloting will allow in-depth ploting rather than wide scale superficial interventions. Staff at Pilot Sites are made available HSS Component is committed and time is coordinated to meet deliverable schedule time periods The decentralization process is completed successfully and staff are motivated |
|  |  | EH Department DHMTs, CHAL & LRCS |  | 2.3.8 Outsourcing and contract management training conducted if relevant | Course on outsourcing and contract management (?) | Dependent on whether outsourcing is agreed – to be confirmed |
| 2.4 | Management and staff in pilot HCFs able to implement and sustain proper HCWM system. Objective: To capacitate the staff of pilot sites so that replication to other districts is assured. | EH Department DHMTs, CHAL & LRCS | - Involve EH and DHMT’ staff and ensure availability of pilot HCFs | 2.4.1 Pilot implemented through DHMTs 2.4.1 Visits to Pilot HCFs 2.4.2 Training and coaching at pilot sites conducted |  | Staff at Pilot sites are made available There is strong cooperation and coordination between the HSS Component and the HCWM Project |
| 2.5 | Exit strategy elaborated and implemented by project end Objective: To ensure sustainability of the project | MoHSW, Line Ministries and DHMTs and HC Facility staff HR Depts HSS Component | Involvement of counterpart staff | 2.5.1 Strategy exit document developed 2.5.1 Counterpart staff consulted 2.5.1 Exit strategy implemented in conjunction with pilot implementation (Link with 2.3 & 2.4) 2.5.1 Exit strategy implementation evaluated | Exit strategy document Evaluation report of exit strategy in Final Completion Report | Capacity within the MoHSW is sufficient and available to implement the exit strategy |

Output 3 :  			Public Awareness and Training

Immediate Objective 1 : 	The public in general and staff of HCFs in particular are aware of the legal framework governing HCW Management as well as of proper HCW Management Practices.

| Output No | Description of Outputs and Objective | Stakeholders | Stakeholder input | Indicators |  | Critical Assump-tions and Risks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Means of Verification | Milestone Deliverable |  |
| 3.1 | Private sector informed about opportunities for private sector participation in HCWM | MoHSW, EH, DHMTs HC Facilities, CHAL & LRCS Private Industry | - Assist with Identifying private industries presently operative in Lesotho | 3.1.1 Information Package designed and consulted with stakeholders | Information package for Private Sector | There is strong cooperation and coordination between the HSS Component and the HCWM Project |
| 3.2 | All Depts within MoHSW are aware of the need of proper HCWM and know the importance of proper HCWM for their own core activities and tasks. | MoHSW, EH, Clinical Services DHMTs; HC Facilities, CHAL & LRCS; HR Department MCA Gender and Social Depts BTS; CLS NDSO | - Identify participants for ½ day workshop - Arrange ½ day workshops | 3.2.1 Common ground analyzed in consultation with Stakeholders 3.2.2 Information packages for each department prepared 3.2.2 ½ day workshop for each department conducted Completed checklists | Information packages for each department in MoHSW: Primary Health Care (with EHD), Clinical Services; HIV/Aids Directorates | HSS Component is committed and time is coordinated to meet deliverable schedule time periods. HSS Component have sufficient budget for the printing of all the information packs |
| 3.3 | General public is aware of the risks of infection when coming into contact with HCRW and of measures for waste related infection prevention | MoHSW: EH, HR, Clinical Services DHMTs; HCFs & Community Health Workers (CHWs), CHAL & LRCS MCA Gender and Social Depts MoHSW HIV/ AIDS unit HPIU Info & Outreach Specialist COWMAN & NHCWMC Trad Doctors, Home Based Care, Pharmacies |  | Information package Interview with residents near HFCs and with visitors and patients in HCFs and via HCWs in community | Information package for General Public. | Message is received favorably Interaction with the General Public has the desired effect. |
| 3.4 | Healthcare professional and support staff of HCFs have sufficient knowledge and understanding of the principles and procedures for HCWM | MoHSW, EH, HR DHMTs HC Facilities, CHAL & LRCS BTS and CLS [HC Committees at HCFs] MCA Gender and Social Depts HSS Component COWMAN & NHCWMC MoHSW HIV/ AIDS unit | Cooperation with and sharing of information and work schedules by HSS [HSS Task 1.1-1.3: 5-yr in-service and Continuing Education Implementation Programme; Develop, produce and distribute resource materials, guidelines and manuals] | 3.4.1 Target groups identified 3.4.2 Curricula training for medical staff at 4 training institutions reviewed in collaboration with HSS Component 3.4.3 Multi-year awareness programme public | Information packages for different target groups of Health Care professional | There is strong cooperation and coordination between the HSS Component and the HCWM Project HSS Component have sufficient budget for the printing of all the information packs |