## Revised Working Programme
Health Care Waste Management Technical Assistance - Technical Proposal | [13 empty] | TECH-10: Work and Deliverables Schedule
Months after Contract Award
|  |  |  | 2009 |  |  | 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013
|  |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
| ACTIVITIES / TASKS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
|  | Component 0 - Project Mobilisation and Inception | Resp.
| 0.1 | Mobilise staff, establish project office and head office backstopping arrangements
| 0.2 | Prepare Inception Report and Update Work Plan
Component 1 - Policy and Legal Framework
| 1.1 | Prepare report on situation analysis of health care waste (Environmental Assessment)
| 1.2 | Develop HCWM Policy
| 1.3 | Elaborate updated National Health Care Waste Management Plan
| 1.4 | Prepare HCWM regulations
| 1.5 | Prepare HCWM standards
| 1.6 | Review and improve HCWM guidelines developed by Environmental Health Department
| 1.7 | Develop Monitoring, Evaluation and Environmental Management System
| 1.8 | Develop licensing and accreditation procedures of Health Facilities
Component 2 - Capacity Building and Knowledge Transfer
| 2.1 | Agree on institutional arrangements for HCWM
| 2.2 | Provide MoHSW, line Ministries and DHMTs with the tools to implement proper HCWM
| 2.3 | Teach MoHSW, line Ministries and DHMTs how to implement the updated NHCWMP
| 2.3.3 | Design HCWM Course and follow up course and train
| 2.3.5 | Pilot Implementation of proper HCWM in sample Districts (and 2.4.1)
| 2.3.6 | Monitoring and Evaluation and reporting uing data collection system
| 2.4 | On-the-job coaching of management and staff to implement and sustain proper HCWM system
| 2.5 | Elaborate and implement an exit strategy
Component 3 - Public Awareness and Training
| 3.1 | Inform private sector about opportunities for private sector participation in HCWM
| 3.2 | Make departments of MoHSW aware of the need of proper HCWM at all levels
| 3.3 | Make general public aware of the dangers of HCWM regarding infectious waste
| 3.4 | Provide knowledge/understanding of proper HCWM to staff of HCFs
Deliverables and Milestones
Management Reports:
Mobilisation Plan | bar: 2009 Oct 1
|  | Inception Report and Work Plan | Janet | bar: 2009 Nov 2
|  | Progress (Quarterly) Reports | Janet | bar: 2010 Feb 5; 2010 May 8; 2010 Nov 14; 2011 Feb 17; 2011 May 20; 2011 Nov 26; 2012 Feb 29; 2012 May 32; 2012 Nov 38
|  | Monthly Reports | Janet | bar: 2009 Dec 3 to 2010 Jan 4; 2010 Mar 6 to 2010 Apr 7; 2010 Jun 9 to 2010 July 10; 2010 Sept 12 to 2010 Oct 13; 2010 Dec 15 to 2011 Jan 16; 2011 Mar 18 to 2011 Apr 19; 2011 Jun 21 to 2011 July 22; 2011 Sept 24 to 2011 Oct 25; 2011 Dec 27 to 2012 Jan 28; 2012 Mar 30 to 2012 Apr 31; 2012 Jun 33 to 2012 July 34; 2012 Sept 36 to 2012 Oct 37; 2012 Dec 39
|  | Annual Report | Janet | bar: 2010 Aug 11; 2011 Aug 23; 2012 Aug 35
|  | Project Completion Report - Draft | Janet | bar: 2013 Jan 40
|  | Project Completion Report - Final | Janet | bar: 2013 Mar 42
Component 1:
|  | Situational analysis of Health Care Waste Report (Output 1.1) | Janet | bar: 2010 May 8
|  | HCWM Policy document (Output 1.2) | Janet | bar: 2010 Jun 9
|  | Updated National Health Care Waste Management Plan (Output 1.3) | Janet | bar: 2010 Sept 12
|  | HCWM regulations (Output 1.4) | Janet | bar: 2011 Mar 18
|  | HCWM standards (Output 1.5) | Janet | bar: 2011 Jun 21
|  | HCWM guidelines (Output 1.6) | Janet | bar: 2011 Sept 24
|  | Environmental Monitoring and Action Plans (Output 1.7) | Janet | bar: 2011 Dec 27
|  | Licensing and accreditation procedures (Output 1.8) | June | bar: 2012 Mar 30
Component 2:
|  | Document on institutional arrangements for HCWM (Output 2.1) | June | bar: 2010 Sept 12
|  | Tools and procedures for implementation and maintenance of HCWM (Output 2.2) | June | bar: 2011 Dec 27
|  | Training course manuals etc. (Output 2.3) | June | bar: 2012 Dec 39
|  | Training documents etc. (Output 2.4) | June | bar: 2013 Mar 42
|  | Exit Strategy (Output 2.5) | Torben | bar: 2012 Jan 28
Component 3:
|  | Information package for the private sector (Output 3.1) | June | bar: 2010 Dec 15
|  | Information package for the departments of MoHSW (Output 3.2) | June | bar: 2011 Jun 21
|  | Information package for the general public (Output 3.3) | June | bar: 2012 Jun 33
|  | Information packages for HCF staff; Multi-year programme etc. (Output 3.4) | June | bar: 2013 Mar 42

## Working Programme showing chang
Health Care Waste Management Technical Assistance - Technical Proposal | [13 empty] | TECH-10: Work and Deliverables Schedule
Months after Contract Award
|  |  |  | 2009 |  |  | 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013
|  |  |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
| ACTIVITIES / TASKS |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
|  | Component 0 - Project Mobilisation and Inception | Resp.
| 0.1 | Mobilise staff, establish project office and head office backstopping arrangements
| 0.2 | Prepare Inception Report and Update Work Plan
Component 1 - Policy and Legal Framework
| 1.1 | Prepare report on situation analysis of health care waste (Environmental Assessment)
| 1.2 | Develop HCWM Policy
| 1.3 | Elaborate updated National Health Care Waste Management Plan
| 1.4 | Prepare HCWM regulations
| 1.5 | Prepare HCWM standards
| 1.6 | Review and improve HCWM guidelines developed by Environmental Health Department
| 1.7 | Develop Monitoring, Evaluation and Environmental Management System
| 1.8 | Develop licensing and accreditation procedures of Health Facilities
Component 2 - Capacity Building and Knowledge Transfer
| 2.1 | Agree on institutional arrangements for HCWM
| 2.2 | Provide MoHSW, line Ministries and DHMTs with the tools to implement proper HCWM
| 2.3 | Teach MoHSW, line Ministries and DHMTs how to implement the updated NHCWMP
| 2.3.3 | Design HCWM Course and follow up course and train
| 2.3.5 | Pilot Implementation of proper HCWM in sample Districts (and 2.4.1)
| 2.3.6 | Monitoring and Evaluation and reporting uing data collection system
| 2.4 | On-the-job coaching of management and staff to implement and sustain proper HCWM system
| 2.5 | Elaborate and implement an exit strategy
Component 3 - Public Awareness and Training
| 3.1 | Inform private sector about opportunities for private sector participation in HCWM
| 3.2 | Make departments of MoHSW aware of the need of proper HCWM at all levels
| 3.3 | Make general public aware of the dangers of HCWM regarding infectious waste
| 3.4 | Provide knowledge/understanding of proper HCWM to staff of HCFs
Deliverables and Milestones
Management Reports:
Mobilisation Plan | bar: 2009 Oct 1
|  | Inception Report and Work Plan | Janet | bar: 2009 Nov 2
|  | Progress (Quarterly) Reports | Janet | bar: 2010 Feb 5; 2010 May 8; 2010 Aug 11; 2010 Nov 14; 2011 Feb 17; 2011 May 20; 2011 Aug 23; 2011 Nov 26; 2012 Feb 29; 2012 May 32; 2012 Aug 35; 2012 Nov 38; 2013 Feb 41
|  | Monthly Reports | Janet | bar: 2009 Dec 3 to 2010 Jan 4; 2010 Mar 6 to 2010 Apr 7; 2010 Jun 9 to 2010 July 10; 2010 Sept 12 to 2010 Oct 13; 2010 Dec 15 to 2011 Jan 16; 2011 Mar 18 to 2011 Apr 19; 2011 Jun 21 to 2011 July 22; 2011 Sept 24 to 2011 Oct 25; 2011 Dec 27 to 2012 Jan 28; 2012 Mar 30 to 2012 Apr 31; 2012 Jun 33 to 2012 July 34; 2012 Sept 36 to 2012 Oct 37; 2012 Dec 39
|  | Annual Report | Janet | bar: 2010 Aug 11 to 2010 Sept 12; 2011 Aug 23 to 2011 Sept 24; 2012 Aug 35 to 2012 Sept 36
|  | Project Completion Report - Draft | Janet | bar: 2013 Jan 40
|  | Project Completion Report - Final | Janet | bar: 2013 Mar 42 to 2013 Apr 43
Component 1:
|  | Situational analysis of Health Care Waste Report (Output 1.1) | Janet | bar: 2010 Mar 6; 2010 May 8
|  | HCWM Policy document (Output 1.2) | Janet | bar: 2010 May 8 to 2010 Jun 9
|  | Updated National Health Care Waste Management Plan (Output 1.3) | Janet | bar: 2010 July 10; 2010 Sept 12
|  | HCWM regulations (Output 1.4) | Janet | bar: 2011 Mar 18
|  | HCWM standards (Output 1.5) | Janet | bar: 2011 Jun 21
|  | HCWM guidelines (Output 1.6) | Janet | bar: 2011 Sept 24
|  | Environmental Monitoring and Action Plans (Output 1.7) | Janet | bar: 2011 Dec 27
|  | Licensing and accreditation procedures (Output 1.8) | June | bar: 2012 Mar 30
Component 2:
|  | Document on institutional arrangements for HCWM (Output 2.1) | June | bar: 2010 Sept 12; 2010 Nov 14
|  | Tools and procedures for implementation and maintenance of HCWM (Output 2.2) | June | bar: 2011 Dec 27
|  | Training course manuals etc. (Output 2.3) | June | bar: 2012 Dec 39
|  | Training documents etc. (Output 2.4) | June | bar: 2013 Mar 42
|  | Exit Strategy (Output 2.5) | Torben | bar: 2012 Jan 28; 2012 Mar 30
Component 3:
|  | Information package for the private sector (Output 3.1) | June | bar: 2010 Dec 15
|  | Information package for the departments of MoHSW (Output 3.2) | June | bar: 2011 Jun 21
|  | Information package for the general public (Output 3.3) | June | bar: 2012 Jun 33
|  | Information packages for HCF staff; Multi-year programme etc. (Output 3.4) | June | bar: 2013 Mar 42

## Working Programme Janet
Health Care Waste Management Technical Assistance - Technical Proposal | [12 empty] | TECH-10: Work and Deliverables Schedule
Months after Contract Award
| ACTIVITIES / TASKS |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Component 0 - Project Mobilisation and Inception
| 0.1 | Mobilise staff, establish project office and head office backstopping arrangements
| 0.2 | Prepare Inception Report and Update Work Plan
Component 1 - Policy and Legal Framework
| 1.1 | Prepare report on situation analysis of health care waste (Environmental Assessment)
| 1.2 | Develop HCWM Policy
| 1.3 | Elaborate updated National Health Care Waste Management Plan
| 1.4 | Prepare HCWM regulations
| 1.5 | Prepare HCWM standards
| 1.6 | Review and improve HCWM guidelines developed by Environmental Health Department
| 1.7 | Develop Monitoring, Evaluation and Environmental Management System
| 1.8 | Develop licensing and accreditation procedures of Health Facilities
Component 2 - Capacity Building and Knowledge Transfer
| 2.1 | Agree on institutional arrangements for HCWM
| 2.2 | Provide MoHSW, line Ministries and DHMTs with the tools to implement proper HCWM
| 2.3 | Teach MoHSW, line Ministries and DHMTs how to implement the updated NHCWMP
| 2.4 | Train management and staff in pilot HCFs to implement and sustain proper HCWM system
| 2.5 | Elaborate and implement an exit strategy
Component 3 - Public Awareness and Training
| 3.1 | Inform private sector about opportunities for private sector participation in HCWM
| 3.2 | Make departments of MoHSW aware of the need of proper HCWM at all levels
| 3.3 | Make general public aware of the dangers of HCWM regarding infectious waste
| 3.4 | Provide knowledge/understanding of proper HCWM to staff of HCFs
Deliverables and Milestones
Management Reports:
Inception Report and Work Plan | bar: Months after Contract Award 2
Progress Reports | bar: Months after Contract Award 5; Months after Contract Award 8; Months after Contract Award 11; Months after Contract Award 14; Months after Contract Award 17; Months after Contract Award 20; Months after Contract Award 23; Months after Contract Award 26; Months after Contract Award 29; Months after Contract Award 32; Months after Contract Award 35; Months after Contract Award 38; Months after Contract Award 41
Monthly Reports | bar: Months after Contract Award 3 to Months after Contract Award 4; Months after Contract Award 6 to Months after Contract Award 7; Months after Contract Award 9 to Months after Contract Award 10; Months after Contract Award 13; Months after Contract Award 15 to Months after Contract Award 16; Months after Contract Award 18 to Months after Contract Award 19; Months after Contract Award 21 to Months after Contract Award 22; Months after Contract Award 25; Months after Contract Award 27 to Months after Contract Award 28; Months after Contract Award 30 to Months after Contract Award 31; Months after Contract Award 33 to Months after Contract Award 34; Months after Contract Award 37; Months after Contract Award 39
Annual Report | bar: Months after Contract Award 12; Months after Contract Award 24; Months after Contract Award 36
Project Completion Report - Draft | bar: Months after Contract Award 40
Project Completion Report - Final | bar: Months after Contract Award 43
Component 1:
Situational analysis of Health Care Waste Report (Output 1.1) | bar: Months after Contract Award 6
HCWM Policy document (Output 1.2) | bar: Months after Contract Award 8
Updated National Health Care Waste Management Plan (Output 1.3) | bar: Months after Contract Award 10
HCWM regulations (Output 1.4) | bar: Months after Contract Award 18
HCWM standards (Output 1.5) | bar: Months after Contract Award 21
HCWM guidelines (Output 1.6) | bar: Months after Contract Award 24
Environmental Monitoring and Action Plans (Output 1.7) | bar: Months after Contract Award 27
Licensing and accreditation procedures (Output 1.8) | bar: Months after Contract Award 30
Component 2:
Document on institutional arrangements for HCWM (Output 2.1) | bar: Months after Contract Award 12
Tools and procedures for implementation and maintenance of HCWM (Output 2.2) | bar: Months after Contract Award 27
Training course manuals etc. (Output 2.3) | bar: Months after Contract Award 39
Training documents etc. (Output 2.4) | bar: Months after Contract Award 42
Exit Strategy (Output 2.5) | bar: Months after Contract Award 30
Component 3:
Information package for the private sector (Output 3.1) | bar: Months after Contract Award 15
Information package for the departments of MoHSW (Output 3.2) | bar: Months after Contract Award 21
Information package for the general public (Output 3.3) | bar: Months after Contract Award 33
Information packages for HCF staff; Multi-year programme etc. (Output 3.4) | bar: Months after Contract Award 42
Note on F19: Janet Magner: There is a need for the capacity component to have input into the situational analysis and I would suggest that this component start earlier
Note on N20: Janet Magner: The tools to implement can only start after the standards and guidelines have been written and approved.
Note on N21: Janet Magner: This Activity can start here as it is an assessment first of the skills levels and then the development of a HCWM Course, training, monitoring etc.
Note on R5: Janet Magner: I have a serious concern with the timing of this output. There is a great deal that needs to happen for the WMP 1.3.1 - 1.3.10. I would like this to be highlighted as a concern
Note on R11: Janet Magner: I would suggest an extra three months to complet the HCWMP